## Completed Items
Focus Area | Opportunity | Actions | Impact | Date Completed
QUALITY
| Enhance Service Deployment Process | Before large scale migrations to the global hierarchy, undertake formal review of SCCM client health and execute remedation plans
| Enhance Service Deployment Process | Establish requirements for a pilot to help member firms understand and test service capabilities and functionality
| Enhance Service Deployment Process | Undertake a post testing toll gate with STS and member firms at the completion of pilot phase
| Improve member firm engagement in service delivery | Establish working group consisting of member firm and STS personnel to provide input, oversight, and support
| Execute infrastructure upgrades and database optimization | Increase all SQL servers to 96GB
| Execute infrastructure upgrades and database optimization | Drive memory upgrades and migration to SQL Server Enterprise
| Improve monitoring and alerting | Transition SCCM monitoring to the STS UPM Service to provide best-in-class proactive and reactive monitoring and alerting on for service related events
| Patch Exemption Process | Define and communicate Patch Exemption process for Member Firms
| Validate MF SCCM Boundaries | Work with member firms to validate SCCM boundaries, agree on changes and establish bi-annual review process
PERFORMANCE
| Optimize SCCM platform | Schedule monthly SCCM maintenance window to allow service team to apply upgrades and iterative improvements and assist MF with planning
| Define KPIs and targets (MF targets) | Define KPIs to provide clear view of the improvements
SUPPORT
Support | Support Enhancement | Review staff schedules to provide 24/7 ticket management capabilities
| Improve member firm engagement in service delivery | Identify immediate opportunities to incorporate skilled and qualified member firm personnel into the service delivery model
COMMUNICATION

## Current Actions
Focus Area | Opportunity | Actions | Impact | Timing | Owner | Benefits/Comments | Status
QUALITY
Quality | Optimize SCCM platform | SCCM Collection Optimization– Collection Rationalization/ Reduction |  | 2017-09-19 | Amanda Butlett |  | 45%
PERFORMANCE
Performance | Client Health Plan | Provide end to end solution. Meaning support at the end level like fixing Client Health issue, non-deployed patch/packages, fixing outstanding compliance |  | 2017-09-30 | Amanda Butlett |  | 87%
SUPPORT
Support
COMMUNICATION
Communication | Update Service Definition | Clarify scope and approach to: Internet Distribution Points Operating System Deployment DMZ Patching |  | 2017-08-31 | David Bruem |  | 85%
[6 empty] | Average Completion ~ | 72.33%

## Backlog
Focus Area | Opportunity | Actions | Impact | Timing | Benefits | Status
QUALITY
Quality | Expand Service Scope | Provide internet facing distribution points for both patch and application distribution (cloud DP)
| Expand Service Scope | Review approach for patching Linux/Unix based devices |  |  |  | Levarage US solution
| Expand Service Scope | Driver deployment approach
| Expand Service Scope | VHD Deployment (NL)
| Expand Service Scope | Software metering
| Expand Service Scope | Task sequencing
| Expand Service Scope | Orchestration for application patching and common tasks
| Expand Service Scope | Reporting framework/governance (not just patch reporting)
| Expand Service Scope | Service management integration
| Expand Service Scope | Windows 10 Servicing
| Expand Service Scope | Application virutalization (AU + ES)
| Expand Service Scope | OSD Approach
| Expand Service Scope | 3rd Party Patch Deployments (Q3 or 4)
| Expand Service Scope - ISO 27001 | T2_Security breaches due to misuse or human error / V1_Lack of or ineffective configuration change control
| Expand Service Scope | T2_Security breaches due to misuse or human error / V7_Lack of records in administrator and operator logs
| Expand Service Scope | T2_Security breaches due to misuse or human error / V9_Lack of information security responsibilities in job descriptions
| Expand Service Scope | T6_Abuse of rights / V3_Lack of or insufficient software testing
| Expand Service Scope | T6_Abuse of rights / V5_Lack of audit trails
| Expand Service Scope | T6_Abuse of rights / V8_Lack of formal process for access right review
| Expand Service Scope | Monitoring of non-hierarchy SCCM environments
PERFORMANCE
Performance | Distibute workload | Investigate federated model with multiple hierarchies |  |  |  | Project underway
SUPPORT
Support | Support Enhancement | Maintain and utilize knowledge documentation
| Support Enhancement | Automate tickets for non-compliance (apps)
| Support Enhancement | Establish the use of common scripts for recurring workloads
Split the current “Servers Missing or Not Set to Patch in GLB” into two separate graphs
“Servers Missing from GLB” – we want all servers in GLB
“Servers not set to Patch in GLB” – there may be a valid reason not to have them set to patch
COMMUNICATION
Communication